## Backup Cluster
TKC BACKUP CLUSTER (Before Upgrade Day)
TASK | STATUS | DESCRIPTION | Estimate Times | ASSIGNEE | NOTE
Step 1: Create Backup Cluster
Copy YAML from Production cluster | Not started | Get the PRD YAML for backup cluster | 45 Minutes | Geton
Edit value in the YAML file | Not started | To edit the values which need to change |  | Geton | TKC=1.26 OS=Ubuntu
Apply the YAML file for creating new cluster | Not started | To apply new YAML for creating the cluster |  | Geton
Step 2: Install important components
Apply PSA to new cluster | Not started | This action need to do before deploy any applications | 10 minutes | Geton
Connect to TMC | Not started | To connect the cluster with TMC | 15 minutes | Geton | Connect via Cluster Management
Install Contour | Not started | For ingressing the applications | 10 minutes | Geton
Create ExternalIPPool | Not started | Create only this one | 10 minutes | Geton
Ensure the new cluster health | Not started | Check the cluster health | 5 minutes | Geton
Step 3: Deploy Existing Apps
Deploy and check existing application to new cluster | Not started | Deploy the applications to the cluster and set replica=0 | 60 minutes | Geton | Replicas = 0 or Disable contour's svc

## Upgrade Plan
TKC UPGRADE PLAN
TASK | STATUS | DESCRIPTION | Estimate Times | ASSIGNEE | NOTE
Step 1: PSA label Preparation
Get the informations of all namespaces | Not started | Get all namespaces which need to apply PSA | 00:00 AM - 00:10 AM | Geton
Create script or command for applying to namespace | Not started | Bring namespace's name to create a script | 00:10 AM - 00:20 AM | Geton
Apply PSA to all namespaces | Not started | To apply the script | 00:20 AM - 00:30 AM | Geton | except system namespaces
Step 2: Upgrade TKC to 1.25
Ensure cluster health is normal | Not started | Check the cluster health is normal | 00:30 AM - 00:40 AM | Geton
Remove Rancher webhook from the cluster | Not started | Remove or disable rancher webhook for clearing upgrade | 00:40 AM - 00:45 AM | Aeon | kind is mutationwebhook
Edit TKC version to 1.25 via kubectl | Not started | kube edit tkc and change TKR version to 1.25 | 00:45 AM - 01:45 AM | Geton | OS=Ubuntu
Check cluster health after upgraded | Not started | After upgraded, re-check the cluster health | 01:45 AM - 01:50 AM | Geton
Ensure all pods are running | Not started | wait a minute, for checking all pods | 01:50 AM - 01:55 AM | Geton, Aeon
Step 3: Upgrade TKC to 1.26
Ensure cluster health is normal | Not started | Check the cluster health is normal | 02:00 AM - 02:10 AM | Geton
Remove Rancher webhook from the cluster | Not started | Remove or disable rancher webhook for clearing upgrade | 02:10 AM - 02:15 AM | Aeon | kind is mutationwebhook
Edit TKC version to 1.26 via kubectl | Not started | kube edit tkc and change TKR version to 1.26 | 02:15 AM - 03:15 AM | Geton | OS=Ubuntu
Check cluster health after upgraded | Not started | After upgraded, re-check the cluster health | 03:15 AM - 03:20 AM | Geton
Ensure all pods are running | Not started | wait a minute, for checking all pods | 03:20 AM - 03:25 AM | Geton, Aeon
Step 4: Testing
Test public access to application API | Not started | To access ingress URL | 03:25 AM - 03:35 AM | Geton, aeon | Can access to app destination
Test public access to application UI | Not started | To access ingress URL | 03:35 AM - 03:45 AM | Geton, aeon | Can access to app destination

## Enable Cipher
ENABLE CIPHER PLAN
TASK | STATUS | DESCRIPTION | Estimate Times | ASSIGNEE | NOTE
Step 1: Update Configuration on TMC
Edit contour configuration on TMC | Not started | To edit contour configuration | 03:45 AM - 03:55 AM | Geton
Rolling the deployment | Not started | To restart all pods of contour | 03:55 AM - 04:00 AM | Geton
Ensure all pods of contour are running | Not started | Re-check the status | 04:00 AM - 04:10 AM | Geton |  | Upgrade plan
Enable HSTS to each HTTPproxy kind | Not started | Add HSTS to each HTTPproxy and re-apply | 04:10 AM - 04:20 AM

## RollBack Plan
ROLLBACK PLAN
TASK | STATUS | DESCRIPTION | Estimate Times | ASSIGNEE | NOTE
Step 1: Disable the connection from PRD
Change service type of contour | Not started | Change to ClusterIP | 10 minutes | Geton
Down the applications to 0 | Not started | Scale down or delete the pods to 0 | 10 minutes | Geton
Backup and delete Egress | Not started | Delete Egress kind | 15 minutes | Geton
Step 2: Enable the connection from BK
Change service type of contour | Not started | Change to LoadBalacner and fill static IP | 10 minutes | Geton | IP is same the PRD IP
Scale up the applications | Not started | Scale up the pods or deployments | 15 minutes | Geton | Replica Number is same PRD cluster
Apply Egress from YAML template | Not started | To apply YAML file from template which is backup from PRD | 15 minutes | Geton
Step 3: Deploy lastest template
Apply Deployments | Not started | To apply the latest YAML file to BK cluster | 15 minutes | Geton | Use it when old deployment has problem